## Template
Punch list | [7 empty] | Do it on your phone →
Project |  |  |  |  | Unit / area
Walkthrough date |  |  |  |  | Prepared by
Contractor |  |  |  |  | Handover date
| Open |  | In progress |  | Closed |  | Total
# | Location / room | Item description | Trade | Priority | Responsible | Due date | Status | Date closed | Verified by
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200

## Example
Punch list | [7 empty] | Do it on your phone →
Project |  | Pine Ridge Residences |  |  | Unit / area |  | Building A, unit 201
Walkthrough date |  | 10/07/2026 |  |  | Prepared by |  | Sarah Mitchell
Contractor |  | Summit Builders LLC |  |  | Handover date |  | 10/21/2026
| Open |  | In progress |  | Closed |  | Total
# | Location / room | Item description | Trade | Priority | Responsible | Due date | Status | Date closed | Verified by
1 | Living room | Diagonal crack in drywall next to the window. | Architectural | High | Drywall sub | 10/14/2026 | In progress
2 | Main bathroom | Missing grout on floor tile next to the shower. | Architectural | Medium | Tile sub | 10/14/2026 | Closed | 10/12/2026 | S. Mitchell
3 | Kitchen | Leak at the drain pipe joint under the sink. | Plumbing | Critical | General contractor | 10/09/2026 | Closed | 10/09/2026 | S. Mitchell
4 | Main bedroom | Closet door drags on the floor when closing. | Carpentry | Low | Carpenter | 10/18/2026 | Open
5 | Laundry | Outlet missing cover plate. | Electrical | High | Electrician | 10/11/2026 | Open
6 | Balcony | Paint splatter on baseboard. | Paint | Low | Painter | 10/18/2026 | Open
7
8
9
10
11
12
13
14
15
16
17
18
19
20